## GanttChart
MSc thesis Project Schedule | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com
TU Delft
| Project Start Date | 2024-01-04 |  |  |  |  | Display Week | 15 | [7 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43 | [6 empty] | Week 44 | [6 empty] | Week 45 | [6 empty] | Week 46 | [6 empty] | Week 47 | [6 empty] | Week 48
| Project Lead | me | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05 | [6 empty] | 2024-08-12 | [6 empty] | 2024-08-19 | [6 empty] | 2024-08-26 | [6 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02
 | time axis 2024-04-08 to 2024-12-07
WBS | TASK | Type | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-04-08 to 2024-12-07
1 | Literature review
1 | literature review |  |  | 2024-01-04 | 2024-03-01 | 58 | 95% | 42
1.1 | noting Willems' thesis, compiling RL MSc theses |  |  | 2024-01-04 | 2024-01-07 | 4 | 100% | 2
1.1.1 | summarize previous theses |  |  | 2024-01-08 | 2024-01-11 | 4 | 100% | 4
1.1.2 | read Sutton & Barto |  |  | 2024-01-12 | 2024-01-16 | 5 | 100% | 3
1.1.3 | code RL exercises from Sutton & Barto |  |  | 2024-01-15 | 2024-01-16 | 2 | 100% | 2
1.1.4 | gather & study flying-V literature |  |  | 2024-01-17 | 2024-01-20 | 4 | 100% | 3
1.1.5 | gather & study SOTA RL/flight control literature |  |  | 2024-01-20 | 2024-02-03 | 15 | 90% | 10
1.1.6 | draft research objective and question(s) |  |  | 2024-01-17 | 2024-02-03 | 18 | 100% | 13
1.1.7 | spring break | 1 |  | 2024-02-04 | 2024-02-08 | 5 | 100% | 4
1.1.8 | write research plan & literature study |  |  | 2024-02-10 | 2024-02-23 | 14 | 90% | 10
1.1.9 | research methods exam | 1 |  | 2024-02-13 | 2024-02-13 | 1 | 100% | 1
| deadline, proposal delivery | 1 |  | 2024-02-23 | 2024-02-23 | 1 | 100% | 1
| meeting, proposal review | 1 |  | 2024-03-01 | 2024-03-01 | 1 | 100% | 1
2 | Research Phase 1
2 | research phase 2 |  |  | 2024-03-02 | 2024-05-17 | 77 | 30% | 55
2.1 | design nominal and faulty evaluation cases |  |  | 2024-03-02 | 2024-03-06 | 5 | 100% | 3
2.2 | obtain linearized model |  |  | 2024-03-02 | 2024-03-07 | 6 | 100% | 4
2.3 | implement & verify IDHP on lin model |  |  | 2024-03-08 | 2024-03-19 | 12 | 100% | 8
2.4 | implement & verify EtIDHP on lin model |  |  | 2024-03-20 | 2024-04-04 | 16 | 100% | 12
2.5 | implement & verify MsIDHP on lin model |  |  | 2024-04-05 | 2024-04-22 | 18 | 100% | 12
2.6 | implement & verify DSAC on lin model | 2 |  | 2024-04-05 | 2024-04-13 | 9 | 0% | 6
2.7 | integrate DSAC and IDHP implementations | 2 |  | 2024-04-14 | 2024-04-22 | 9 | 0% | 6
2.8 | compile + document preliminary results |  |  | 2024-04-23 | 2024-05-12 | 20 | 5% | 14
2.8.1 | run implementations on evaluation cases |  |  | 2024-04-23 | 2024-04-29 | 7 | 0% | 5
2.8.2 | compile and document performances |  |  | 2024-04-30 | 2024-05-04 | 5 | 0% | 4
2.8.3 | write accompanying texts |  |  | 2024-05-05 | 2024-05-12 | 8 | 0% | 5
| deadline, midterm deliverables | 1 |  | 2024-05-12 | 2024-05-12 | 1 | 100% | 0
| meeting, mid-term | 1 |  | 2024-05-17 | 2024-05-17 | 1 | 100% | 1
3 | Research Phase 2
3 | research phase 2 |  |  | 2024-05-18 | 2024-07-29 | 73 | 0% | 51
3.1 | design nominal & faulty evaluation cases |  |  | 2024-05-18 | 2024-05-21 | 4 | 0% | 2
3.2 | obtain nonlinear model |  |  | 2024-05-18 | 2024-05-24 | 7 | 0% | 5
3.3 | implement/integrate comparison controllers with nonlinear model |  |  | 2024-05-25 | 2024-06-11 | 18 | 0% | 12
3.4 | compile and document results |  |  | 2024-06-12 | 2024-07-13 | 32 | 0% | 23
3.4.1 | run all controllers on evaluation cases |  |  | 2024-06-12 | 2024-06-17 | 6 | 0% | 4
3.4.2 | compile and document performances |  |  | 2024-06-18 | 2024-06-22 | 5 | 0% | 4
3.4.3 | write scientific article, additional results, and accompanying chapters |  |  | 2024-06-23 | 2024-07-13 | 21 | 0% | 15
| deadline, draft submission | 1 |  | 2024-07-24 | 2024-07-24 | 1 | 100% | 1
| meeting, greenlight | 1 |  | 2024-07-29 | 2024-07-29 | 1 | 100% | 1
4 | Research Dissemination
4.1 | research dissemination |  |  | 2024-07-30 | 2024-08-30 | 32 | 0% | 24
4.1.1 | request defence | 1 |  | 2024-08-01 | 2024-08-01 | 1 | 100% | 1
4.1.2 | deadline, thesis upload to repo | 1 |  | 2024-08-16 | 2024-08-16 | 1 | 100% | 1
4.1.3 | defence | 1 |  | 2024-08-30 | 2024-08-30 | 1 | 100% | 1
TEMPLATE ROWS
See the Help worksheet to learn how to use these template rows. You can hide these rows before printing.
1 | [ Level 1 Task, Category, or Phase ] | [7 empty] | 2024-04-29: tim traas- who started september 2022, has the 9 month MSc regulation, INDI for flying-V
1.1 | . [ Level 2 Task ] |  |  |  | - |  | 0% | 0 | 2024-04-29: dirench atmaca - phd indi flying v
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  | 0% | 0 | 2024-04-29: enns apache helicopter I think? Lost notes :(
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  | 0% | 0
► Watch How to Create a Gantt Chart in Excel | [8 empty] | 2024-04-27: greenlight, 1 week for feedback, 1 week for incorporating 2 weeks before defence submit final thesis
Note on A7: Work Breakdown Structure/Work Packages Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Non-workpackage
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.